TEST EFFORT ESTIMATION TOOL

Software Requirements Specification

Version 1.0 – Draft

2026-02-26

| Document Title | Test Effort Estimation Tool – Software Requirements Specification |
| --- | --- |
| Version | 1.0 – Draft |
| Author | Test Engineering Team |
| Date | 2026-02-26 |
| Status | For Review |

# Table of Contents

1. Introduction

1.1 Purpose

1.2 Scope

1.3 Stakeholders

1.4 Technology Stack

2. Data Model

2.1 Entity Relationship Overview

2.2–2.10 Table Definitions

3. Wizard Workflow

3.1–3.7 Steps 1–7

4. Estimation Calculation Engine

4.1 Core Formula

4.2 Aggregation

4.3 Feasibility Check

4.4 Historical Calibration

4.5 Risk Flags

5. Output Reports

5.1 On-Screen Summary

5.2 PDF / Word Report

5.3 Excel Export

6. User Interface Specifications

7. Implementation Roadmap

8. Appendix

8.1 Sample Task Templates

8.2 Estimation Worked Example

8.3 API Endpoints Summary

# 1. Introduction

## 1.1 Purpose

This document defines the complete software requirements specification for a Test Effort Estimation Tool. The tool enables test managers to quickly and accurately estimate testing effort for new products, evolutions, and support projects by leveraging a structured intake workflow, a predefined task catalog, historical project data, and automated calculation logic.

## 1.2 Scope

The tool covers the full estimation lifecycle: project intake, feature-to-task mapping, effort calculation with multipliers, tester and test leader allocation, timeline feasibility checking, and report generation in multiple formats (on-screen, PDF/Word, Excel).

## 1.3 Stakeholders

| Role | Responsibility | Interaction |
| --- | --- | --- |
| Test Manager | Creates estimations, assigns testers | Primary user – wizard workflow |
| Test Leader | Reviews estimations, supports testers | Reviews generated reports |
| Tester | Executes assigned tasks | Views task assignments |
| Admin | Maintains catalogs and config | Data management interface |

## 1.4 Technology Stack

The tool is built entirely with Python and C# to minimize language fragmentation, simplify maintenance, and streamline deployment. Two deployment options are supported: a desktop application (single executable) and an optional web variant.

### Option A: Desktop Application (Recommended)

| Component | Technology |
| --- | --- |
| Frontend | C# WinForms (.NET 8) – native desktop UI, single .exe deployment |
| Backend Logic | Python (embedded via pythonnet or subprocess IPC) – calculation engine and report generation |
| Database | SQLite via System.Data.SQLite (C#) and sqlite3 (Python) – single file, no server |
| Reports | PDF (WeasyPrint or ReportLab), Word (python-docx), Excel (openpyxl) |
| Packaging | C# published as single-file .exe; Python bundled via embedded runtime or PyInstaller |

### Option B: Web Application

| Component | Technology |
| --- | --- |
| Frontend | Python (Streamlit or NiceGUI) – pure Python web UI, no JS required |
| Backend API | Python (FastAPI) – REST API serving estimation logic |
| Database | SQLite via sqlite3 / SQLAlchemy – single file, no server |
| Reports | PDF (WeasyPrint or ReportLab), Word (python-docx), Excel (openpyxl) |
| Deployment | Single Docker container or direct pip install + run |

### Technology Decision Rationale

- Python-only backend: All calculation logic, report generation, and data access in one language – no context switching for developers maintaining the codebase

- C# WinForms for desktop: Native Windows UI familiar to testers, easy deployment as single .exe, direct SQLite access for fast local operation

- Python web frontend (Streamlit/NiceGUI): If web access is needed, avoids introducing JavaScript entirely – the full stack remains Python

- SQLite: Zero-configuration database, portable (single .db file can be backed up or shared), sufficient for team-scale usage

- Report libraries are all Python-native: python-docx, openpyxl, and WeasyPrint/ReportLab are mature, well-maintained, and produce professional output

### Inter-Process Communication (Desktop Option A)

The C# frontend communicates with the Python backend via one of these approaches:

- Subprocess IPC (recommended): C# launches Python scripts and exchanges data via JSON over stdin/stdout. Simple, debuggable, no dependencies.

- REST API (local): Python runs a lightweight FastAPI server on localhost; C# calls it via HttpClient. Better for complex async operations.

- pythonnet: Direct in-process Python execution from C#. Tightest integration but adds deployment complexity.

# 2. Data Model

All data is stored in a SQLite database. Below are the core entities and their schemas.

## 2.1 Entity Relationship Overview

The data model consists of 9 core tables organized around projects, features, tasks, and team allocation. The relationships follow this hierarchy: Projects reference Features, Features map to Task Templates, and Estimations combine Projects with calculated Task Assignments.

## 2.2 Table: features

Master catalog of testable features. Each feature belongs to a category and has a complexity weight.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| name | TEXT | UNIQUE | Feature name (e.g., "SIM Toolkit", "OTA Update") |
| category | TEXT |  | Grouping category (e.g., "Telecom", "Security") |
| complexity_weight | REAL |  | 1.0 = standard, 1.5 = complex, 2.0 = very complex |
| has_existing_tests | BOOLEAN |  | Whether premade tests exist for this feature |
| description | TEXT |  | Detailed description of the feature scope |
| created_at | DATETIME |  | Record creation timestamp |

## 2.3 Table: task_templates

Predefined tasks linked to features. Each template stores the base effort in hours for one tester.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| feature_id | INTEGER | FK | References features.id |
| name | TEXT |  | Task name (e.g., "Execute regression suite") |
| task_type | TEXT |  | SETUP ¦ EXECUTION ¦ ANALYSIS ¦ REPORTING ¦ STUDY |
| base_effort_hours | REAL |  | Base effort for 1 tester, 1 DUT, 1 profile |
| scales_with_dut | BOOLEAN |  | If true, effort multiplied by DUT count |
| scales_with_profile | BOOLEAN |  | If true, effort multiplied by profile count |
| is_parallelizable | BOOLEAN |  | Can be split across multiple testers |
| description | TEXT |  | Detailed task description |

## 2.4 Table: dut_types

Registry of device types with their test complexity multiplier.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| name | TEXT | UNIQUE | Device name/model |
| category | TEXT |  | Device category (SIM, eSIM, UICC, etc.) |
| complexity_multiplier | REAL |  | 1.0 = standard, higher = more effort per test |

## 2.5 Table: test_profiles

Test configuration profiles that define execution parameters.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| name | TEXT | UNIQUE | Profile name |
| description | TEXT |  | Profile configuration details |
| effort_multiplier | REAL |  | Multiplier applied to tasks scaling with profiles |

## 2.6 Table: historical_projects

Archive of past projects with actual effort data for calibration and reference.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| project_name | TEXT |  | Project identifier/name |
| project_type | TEXT |  | NEW ¦ EVOLUTION ¦ SUPPORT |
| estimated_hours | REAL |  | Original estimated total hours |
| actual_hours | REAL |  | Actual hours spent (post-completion) |
| dut_count | INTEGER |  | Number of DUTs used |
| profile_count | INTEGER |  | Number of test profiles |
| pr_count | INTEGER |  | Number of PR fixes |
| features_json | TEXT |  | JSON array of feature IDs tested |
| completion_date | DATE |  | Project completion date |
| notes | TEXT |  | Lessons learned / deviation notes |

## 2.7 Table: estimations

Core estimation records – one per estimation session.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| project_name | TEXT |  | Name of the project being estimated |
| project_type | TEXT |  | NEW ¦ EVOLUTION ¦ SUPPORT |
| reference_project_ids | TEXT |  | JSON array of historical_projects.id references |
| dut_count | INTEGER |  | Number of DUTs |
| profile_count | INTEGER |  | Number of test profiles |
| dut_profile_combinations | INTEGER |  | Actual DUT × Profile combinations to test |
| pr_fix_count | INTEGER |  | Number of PR fixes |
| expected_delivery | DATE |  | Target delivery date |
| total_tester_hours | REAL |  | Calculated total tester effort |
| total_leader_hours | REAL |  | Calculated test leader effort (50% of tester) |
| grand_total_hours | REAL |  | Sum of all effort |
| feasibility_status | TEXT |  | FEASIBLE ¦ AT_RISK ¦ NOT_FEASIBLE |
| created_at | DATETIME |  | Estimation creation timestamp |
| created_by | TEXT |  | Manager who created the estimation |

## 2.8 Table: estimation_tasks

Individual task breakdown within an estimation, with tester allocation.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| estimation_id | INTEGER | FK | References estimations.id |
| task_template_id | INTEGER | FK | References task_templates.id (NULL if custom) |
| task_name | TEXT |  | Task name (from template or custom) |
| task_type | TEXT |  | SETUP ¦ EXECUTION ¦ ANALYSIS ¦ REPORTING ¦ STUDY |
| base_hours | REAL |  | Base effort before multipliers |
| calculated_hours | REAL |  | Final effort after multipliers |
| assigned_testers | INTEGER |  | Number of testers assigned |
| has_leader_support | BOOLEAN |  | Whether test leader supports this task |
| leader_hours | REAL |  | Test leader effort (50% of tester hours) |
| is_new_feature_study | BOOLEAN |  | Flagged as new feature study task |
| notes | TEXT |  | Additional notes or assumptions |

## 2.9 Table: team_members

Available testers and test leaders with capacity information.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| id | INTEGER | PK | Auto-increment primary key |
| name | TEXT |  | Team member name |
| role | TEXT |  | TESTER ¦ TEST_LEADER |
| available_hours_per_day | REAL |  | Daily available hours (default 7) |
| skills_json | TEXT |  | JSON array of feature IDs they are skilled in |

## 2.10 Table: configuration

Global configuration parameters for the estimation engine.

| Column | Type | Key | Description |
| --- | --- | --- | --- |
| key | TEXT | PK | Configuration key name |
| value | TEXT |  | Configuration value |
| description | TEXT |  | What this setting controls |

Default configuration values:

- leader_effort_ratio: 0.5 (test leader gets 50% of tester effort)

- pr_fix_base_hours: 4.0 (average hours per PR fix for testing)

- new_feature_study_hours: 16.0 (hours to study and create tests for a new feature)

- working_hours_per_day: 7.0 (productive hours per working day)

- buffer_percentage: 10 (additional percentage buffer for unknowns)

# 3. Wizard Workflow

The estimation process follows a 7-step wizard. Each step collects specific input, and the UI dynamically adapts based on selections in previous steps.

## 3.1 Step 1: Project Type

The manager selects one of three project types. This controls which questions appear in subsequent steps.

| Type | Description | Next Step Behavior |
| --- | --- | --- |
| NEW | Brand new product requiring full test creation | Show full feature catalog; flag all as new study tasks |
| EVOLUTION | Existing product with new features added | Show features from reference project + new feature selection |
| SUPPORT | Maintenance/fix release for existing product | Show only PR fix section + regression scope selection |

## 3.2 Step 2: Feature Selection

Conditional display based on project type:

- NEW: Full feature catalog displayed as checklist. All selected features are flagged as requiring new test study effort.

- EVOLUTION: Features from reference project pre-selected. Manager adds new features from catalog and marks which are genuinely new (requiring study). Removed features can be unchecked.

- SUPPORT: Feature selection is limited to the scope of regression testing. Manager selects which areas are impacted by the PR fixes.

For each selected feature, the system automatically maps to available task templates. Features without existing tests are flagged, and a "Study and Create Tests" task is auto-added.

## 3.3 Step 3: Reference Projects

The manager can link one or more historical projects for baseline comparison. The system displays:

- Previous project estimated vs. actual hours (accuracy ratio)

- Feature overlap percentage with the current project

- DUT and profile counts from the reference for comparison

- Auto-suggested adjustment factor based on historical accuracy

## 3.4 Step 4: DUT and Profile Matrix

The manager defines the test matrix:

- Select DUT types from the registry (or add new ones)

- Select test profiles from the catalog (or add new ones)

- Define the DUT × Profile combination matrix – not all combinations may be needed

- The system calculates total combinations and displays the matrix as a grid

Example: 3 DUTs × 4 profiles = 12 possible combinations, but manager might select only 8 relevant ones.

## 3.5 Step 5: PR Fixes

For all project types (but especially SUPPORT):

- Enter total number of PR fixes to be validated

- Optionally categorize by complexity: Simple (2h), Medium (4h), Complex (8h)

- System calculates total PR validation effort

- For SUPPORT projects, this is the primary effort driver alongside regression

## 3.6 Step 6: Delivery Date and Team

The manager enters the target delivery date and available team:

- Expected delivery date (calendar picker)

- Number of available testers (or select specific team members)

- Whether a test leader is assigned (0 or 1)

- Any known constraints (holidays, partial availability)

## 3.7 Step 7: Review and Generate

The system presents a complete estimation summary with:

- Task-by-task effort breakdown table

- Tester allocation per task

- Test leader overhead calculation

- New feature study hours (flagged separately)

- PR fix validation hours

- Grand total in person-hours and person-days

- Timeline feasibility check with risk flags

- Comparison with reference project(s) if linked

The manager can adjust any values before finalizing. Once confirmed, the estimation is saved and reports can be exported.

# 4. Estimation Calculation Engine

## 4.1 Core Formula

For each task in the estimation, the effort is calculated as follows:

Task_Effort = Base_Hours × DUT_Multiplier × Profile_Multiplier × Complexity_Weight

Where:

- Base_Hours: From task_templates.base_effort_hours

- DUT_Multiplier: If scales_with_dut is true → number of DUTs; otherwise 1

- Profile_Multiplier: If scales_with_profile is true → number of profiles; otherwise 1

- Complexity_Weight: From features.complexity_weight

## 4.2 Aggregation

Total_Tester_Effort  = Σ(all task efforts)

Test_Leader_Effort   = Total_Tester_Effort × leader_effort_ratio

PR_Fix_Effort        = Σ(PR_count_by_complexity × hours_per_complexity)

New_Feature_Study    = New_Feature_Count × new_feature_study_hours

Buffer               = Subtotal × buffer_percentage / 100

GRAND TOTAL = Tester + Leader + PR_Fix + Study + Buffer

## 4.3 Feasibility Check

The system checks if the estimation is achievable within the timeline:

Available_Capacity = Working_Days × Team_Size × Hours_Per_Day

| Status | Condition | Action |
| --- | --- | --- |
| FEASIBLE | Grand Total ≤ 80% of Available Capacity | Green indicator – comfortable margin |
| AT_RISK | Grand Total between 80%-100% of Capacity | Amber indicator – warn about tight schedule |
| NOT_FEASIBLE | Grand Total > 100% of Available Capacity | Red indicator – suggest adding team or extending date |

## 4.4 Historical Calibration

When reference projects are linked, the system calculates an accuracy factor:

Accuracy_Ratio = Actual_Hours / Estimated_Hours  (from reference projects)

If the average accuracy ratio across reference projects is above 1.0 (we consistently underestimate), the system suggests applying the ratio as an adjustment factor and displays a warning. This is optional and the manager decides whether to apply it.

## 4.5 Risk Flags

The system automatically flags the following risk conditions:

- More than 50% of features are new (no existing tests) – high estimation uncertainty

- No reference projects linked – no baseline for comparison

- Delivery date is less than 2 weeks away – compressed timeline risk

- DUT × Profile combinations exceed 20 – high matrix complexity

- Historical accuracy ratio > 1.3 – team tends to significantly underestimate

# 5. Output Reports

The tool generates three types of output, all containing the same estimation data in different formats.

## 5.1 On-Screen Summary

Displayed immediately after Step 7 of the wizard. Interactive dashboard with:

- Estimation overview card (project name, type, total hours, feasibility status)

- Task breakdown table (sortable, filterable by task type)

- DUT × Profile matrix heatmap showing effort distribution

- Timeline Gantt-style bar showing effort vs. available time

- Reference project comparison side panel

- Risk flags displayed as alert banners

## 5.2 PDF / Word Report

Formal estimation document suitable for sharing with project stakeholders. Contains:

- Cover page with project name, estimation ID, date, and author

- Executive summary (total effort, feasibility, key risks)

- Project parameters table (type, DUTs, profiles, PR count, delivery date)

- Detailed task breakdown table with all columns

- Tester allocation summary

- Timeline feasibility analysis

- Reference project comparison (if linked)

- Assumptions and risk flags

## 5.3 Excel Export

Editable spreadsheet for managers who need to fine-tune or present data in meetings:

- Sheet 1 – Summary: Key metrics and totals

- Sheet 2 – Task Breakdown: Full task list with all calculation columns, editable effort values

- Sheet 3 – DUT-Profile Matrix: Grid showing combinations and per-combination effort

- Sheet 4 – Team Allocation: Tester assignments with hours per person

- Sheet 5 – PR Fixes: PR breakdown by complexity

- Sheet 6 – Reference Data: Historical project comparison

# 6. User Interface Specifications

## 6.1 Screen Layout

The application uses a sidebar navigation with the following screens:

| Screen | Description |
| --- | --- |
| Dashboard | List of all estimations with status, date, total hours. Search and filter. |
| New Estimation | 7-step wizard (see Section 3) |
| Estimation Detail | View/edit a saved estimation with all reports |
| Feature Catalog | CRUD for features and their linked task templates |
| DUT Registry | CRUD for device types and complexity multipliers |
| Profile Manager | CRUD for test profiles |
| Historical Projects | Browse/import past projects and actual effort data |
| Team Manager | Manage testers, leaders, and their availability |
| Settings | Global configuration parameters |

## 6.2 Wizard UX Guidelines

- Progress indicator showing current step (1–7) at the top

- Back/Next navigation with validation before proceeding

- Auto-save draft state so the wizard can be resumed

- Inline help tooltips explaining each field

- Real-time effort preview panel on the right side (updates as inputs change)

- Keyboard navigation support for power users

# 7. Implementation Roadmap

Recommended phased delivery approach:

## Phase 1: Foundation (Weeks 1–2)

- Set up SQLite database with all tables and seed data (Python script for schema + migrations)

- Implement Python backend: SQLAlchemy models, CRUD operations, and estimation engine module

- Build Feature Catalog and DUT Registry management (C# WinForms CRUD screens or Streamlit pages)

- Import existing premade test templates into task_templates table

- Establish IPC layer between C# frontend and Python backend (JSON over subprocess or local FastAPI)

## Phase 2: Estimation Engine (Weeks 3–4)

- Implement the 7-step wizard UI in C# WinForms (TabControl or panel-based flow) or Streamlit multi-page

- Build Python calculation engine with all formulas (see Section 4)

- Implement feasibility check logic in Python

- On-screen summary display with DataGridView (C#) or Streamlit tables/charts

## Phase 3: Reporting (Weeks 5–6)

- PDF report generation with WeasyPrint or ReportLab (Python)

- Word report generation with python-docx (Python)

- Excel export with openpyxl – multi-sheet formatted workbook (Python)

- Historical project import and calibration logic

## Phase 4: Polish and Deployment (Week 7)

- Team management and tester allocation screens

- Risk flag system and visual indicators

- Package C# app as single-file .exe with embedded Python runtime (or bundle Python via PyInstaller)

- User testing, refinement, and documentation

# 8. Appendix

## 8.1 Sample Task Templates

Below is an example set of task templates that should be pre-loaded into the system. These should be customized based on your team’s actual task definitions.

| Task Name | Type | Base Hrs | DUT? | Profile? | Parallel? |
| --- | --- | --- | --- | --- | --- |
| Environment setup | SETUP | 8 | Yes | No | No |
| Test plan review | SETUP | 4 | No | No | No |
| Execute test suite | EXECUTION | 16 | Yes | Yes | Yes |
| Regression testing | EXECUTION | 12 | Yes | Yes | Yes |
| PR fix validation | EXECUTION | 4 | Yes | No | Yes |
| Result analysis | ANALYSIS | 6 | No | No | No |
| Test report writing | REPORTING | 8 | No | No | No |
| New feature study | STUDY | 16 | No | No | No |
| Test creation | STUDY | 24 | No | No | No |

## 8.2 Estimation Worked Example

Project: "SIM Toolkit v2.5" (EVOLUTION), 3 DUTs, 2 Profiles, 5 PR fixes, 1 new feature, 3 testers + 1 leader, delivery in 4 weeks.

| Task | Base | DUT× | Prof× | Total | Notes |
| --- | --- | --- | --- | --- | --- |
| Environment setup | 8h | ×3 | ×1 | 24h | Per DUT |
| Test plan review | 4h | ×1 | ×1 | 4h | Once |
| Execute test suite | 16h | ×3 | ×2 | 96h | Full matrix |
| Regression testing | 12h | ×3 | ×2 | 72h | Full matrix |
| PR fix validation | 4h×5 | ×3 | ×1 | 60h | 5 PRs × 3 DUTs |
| New feature study | 16h | ×1 | ×1 | 16h | 1 new feature |
| Test creation (new) | 24h | ×1 | ×1 | 24h | 1 new feature |
| Result analysis | 6h | ×1 | ×1 | 6h | Once |
| Test report writing | 8h | ×1 | ×1 | 8h | Once |

Total Tester Effort: 310 hours

Test Leader Effort: 310 × 0.5 = 155 hours

Buffer (10%): 46.5 hours

Grand Total: 511.5 hours (73.1 person-days)

Available Capacity: 20 working days × 4 people × 7 hrs = 560 hours

Utilization: 511.5 / 560 = 91.3% → AT_RISK

The system would flag this as AT_RISK and suggest either extending the delivery date by 1 week or adding 1 more tester to bring utilization below 80%.

## 8.3 API Endpoints Summary

For the web application variant (FastAPI), or the local REST server used by the C# desktop app, the following endpoints should be implemented. In the desktop subprocess IPC variant, these map to Python CLI commands accepting JSON input and returning JSON output.

| Method | Endpoint | Description |
| --- | --- | --- |
| GET | /api/features | List all features with task templates |
| POST | /api/features | Create a new feature |
| GET | /api/dut-types | List all DUT types |
| GET | /api/profiles | List all test profiles |
| GET | /api/historical-projects | List past projects for reference |
| POST | /api/estimations | Create new estimation (full wizard payload) |
| GET | /api/estimations/:id | Get estimation detail with tasks |
| PUT | /api/estimations/:id | Update estimation (adjust values) |
| GET | /api/estimations/:id/report/pdf | Download PDF report |
| GET | /api/estimations/:id/report/docx | Download Word report |
| GET | /api/estimations/:id/report/xlsx | Download Excel export |
| POST | /api/estimations/:id/calculate | Recalculate effort after adjustments |
| GET | /api/team-members | List available testers and leaders |
| GET | /api/configuration | Get global configuration values |